## LRNA
Pakistan Literacy Project [Room to Read] Idara-e-Taleem-o Aagahi (ITA)
Rooms For Libraries Need Assessments , District Bahawalpur
Sr.No. | Tehsil | School Code | School Name | School Gender | Need Assessments | room size in foots | Doors Sizes | Windows Sizes | No. of ceilings need paint | No. of walls need paint | No. of windows need curtains | No. of doors need curtains | No. of windows require locks | No. doors require Locks | No. of ceiling fans required | No. of windows required Mirrors | No. of floors required carpers | No. of Energy Savers required | NO. of fall ceiling required | No. of door mats required | No. of shoe racks require
1 | Bahawalpur Sadar | 3160017 | GHS Dera Bakha | Boys | 1- Paint on four walls, corridor and Ceiling 2- Carpeting on the floor 3- Curtains on 5 windows and 1 door 4- Stationery for the decoration of the room 5- Ceiling fans: 3 6- fall ceiling for the library room. 7- Door mats 8-shoe racks | 15.10X24.9 | 4x8 | 5.5X4 of each window | 1 | 4 | 5 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 2 | 1
9 | Bahawalpur Sadar | 31260053 | GES Chak 5 BC | Boys | 1- Paint on four walls , corridor and Ceiling 2- Carpeting on the floor 3- Curtains on 04 windows and 1 door 4- Stationery for the decoration of the room 5-Ceiling fans:3. 6- Mirrors for windows 10 with size (1.4x1.5) of each. 7-Ceiling fans:3 8- Energy savers:5 9-fall ceiling for the room 10- door mats 11-shoe racks | 17.11X27.10 | 4X7 | 4.6X5.11 | 1 | 4 | 4 | 1 | 0 | 0 | 3 | 10 | 1 | 5 | 1 | 2 | 1
4 | Bahawalpur City | 31220324 | GGES Medical colony | Girls | 1- Paint on 4 walls, front wall and Ceiling 2- Carpeting on the floor 3- Curtains on 4 windows and 1 door 4- Stationery for the decoration of the room 5- Ceiling fans: 3 6-Window locks:12. 7- Electric wiring is needed on two walls to enhance lighting in the room 8- fall ceiling for the library room. 9- Door mats 10-shoe racks | 21.9X17.1 | 4x8.8 | 6X4 of each window | 1 | 4 | 4 | 1 | 12 | 0 | 3 | 0 | 1 | 5 | 1 | 2 | 1
7 | Bahawalpur City | 31220032 | GGHS Canal Colony | Girls | 1- Painting on four walls , corridor and Ceiling 2- Carpeting on the floor 3- Curtains on 05 windows and 1 door 4- Stationery for the decoration of the room 5-Ceilings fans: 3. 6- 3 mirrors on windows with size (1.5X1.2). 7- 3 cracks on the floor need repairing 8-ceiling fans:3 9-Energy savers:6 10- fall ceiling for the library room. 11- Door mats 12-shoe racks | 27.11X18 | 8.6X4 | 4X6 of each window | 1 | 4 | 5 | 1 | 0 | 0 | 3 | 3 | 1 | 6 | 1 | 2 | 1
2 | Bahawalpur Sadar | 31260080 | GGHS 6 BC | Girls | 1- Paint on four walls, corridor and Ceiling 2- Carpeting on the floor 3- Curtains on 4 windows and 1 door 4- Stationery for the decoration of the room 5- 1 window lock 6- Ceiling fans:3 7- 11 mirrors for windows. 8- Fall ceiling for the library room. 9- Door mats 10-shoe racks | 28x17.11 | 7x4 | 4.6x6 of each window | 1 | 4 | 4 | 1 | 1 | 0 | 3 | 11 | 1 | 6 | 1 | 2 | 1
5 | Bahawalpur City | 31220382 | GMPS Awami Colony | Mix | 1- Paint on four walls , corridor and Ceiling 2- Carpeting on the floor 3- Curtains on 3 windows and 1 door 4- Stationery for the decoration of the room 5- 2 mirror for windows with size (1.5X1.1) of each. 6- Window locks: 7 7- Ceiling fans:3 8.Energy savers:5 9- fall ceiling for the library room. 10- Door mats 11-shoe racks 12- windows nets:6 | 27.10X17.10 | 4X7.2 | 4.6x6 of each window | 1 | 4 | 3 | 1 | 7 | 0 | 3 | 2 | 1 | 5 | 1 | 2 | 1
10 | Bahawalpur Sadar | 31260253 | GBHS Khajgan | Boys | 1- Paint on four walls , corridor and Ceiling 2- Carpeting on the floor 3- Curtains on 04 windows and 1 door 4- Stationery for the decoration of the room 5-Need locks on 3 windows. 6- Ceiling fans: 5 7-Eneryg savers:5 8- fall ceiling for the library room. 9- Door mats 10-shoe racks | 27.11X17.11 | 4x8.5 | 3x6 of each window | 1 | 4 | 4 | 1 | 3 | 0 | 5 | 0 | 1 | 5 | 1 | 2 | 1
3 | Yazman | 31240078 | GGES 56 DB | Girls | 1- Paint on four walls , corridor and Ceiling 2- Carpeting on the floor 3- Curtains on 03 windows and 02 doors 4- Stationery for the decoration of the room 5- Ceiling fans: 3 6- 1 mirror for window with size (1.1x 1.3) 7- minor cracks in one wall need repairing. 8- Energy savers: 5 9- fall ceiling for the library room. 10- Door mats 11-shoe racks | 18.2X28.1 | 4x7 of each | 5x4 of each window | 1 | 4 | 3 | 2 | 0 | 0 | 3 | 1 | 1 | 5 | 1 | 2 | 1
8 | Yazman | 31240070 | GGES Christian colony | Girls | 1- Paint on four walls , corridor and Ceiling 2- Carpeting on the floor 3- Curtains on 05 windows and 1 door 4- Stationery for the decoration of the room 5- 3 locks for the windows 6- 1 mirror for window.7-Ceiling fans: 3 8. Energy savers: 5 9- fall ceiling for the library room. 10- Door mats 11-shoe racks | 18X27.9 | 4x8.5 | 6X4 of each window | 1 | 4 | 5 | 1 | 3 | 0 | 3 | 1 | 1 | 5 | 1 | 2 | 1
6 | Bahawalpur Sadar | 31260482 | GMPS Kot dadoo ghaloo | MIx | 1- Paint on four walls , corridor and Ceiling 2- Carpeting on the floor 3- Curtains on 5 windows and 2 doors 4- Stationery for the decoration of the room. 5- Energy Savers:5 6- Ceiling fans: 5. 7- 2 window mirrors with size (1.4x3.7) of each 7- fall ceiling for the library room. 8- Door mats 9-shoe racks | 17.10X27.10 | 3.8X7 of each windows | 5X4 of each window | 1 | 4 | 5 | 2 | 0 | 0 | 5 | 2 | 1 | 5 | 1 | 2 | 1
|  | Total | [6 empty] | 10 | 40 | 42 | 12 | 26 | 0 | 34 | 30 | 10 | 47 | 10 | 20 | 10